## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story / Feature Description | MoSCoW | Dependency | Assignee | Status
1 | 1 | US-1 | Create an intelligent model to categorize support tickets and predict possible resolutions, reducing manual triage effort. | Must |  | Nidhi | Completed
2 | 2 | US-2 | Design a simple interface for customers to log tickets and track progress with clear, real-time updates. | Should | 1 | Nidhi | Completed
3 | 3 | US-3 | Connect the ML engine to the UI so that users and agents get auto-suggestions for quicker resolution | Must | 2 | Nidhi | Completed
4 | 4 | US-4 | Use RAG to analyze ticket text for sentiment and context, enabling prioritization and better response accuracy. | Must | 3 | Nidhi | Completed
5 | 5 | US-5 | Develop a dashboard with metrics, charts, and alerts to help managers monitor team performance and efficiency. | Should | 4 | Nidhi | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | T-01 | ML model for ticket classification & resolution predictionIncludes intent detection and resolution suggestions | 2025-08-13 | 2025-08-17 | Nidhi | Coding | Completed | 8 | Data Collection | Preprocessing | Model Training | Validation | Refinement
2 | T-01a | Integrate AI Agent for automated ticket repliesResponds to simple requests and escalates complex tickets | 2025-08-18 | 2025-08-20 | Nidhi | Coding | Completed | 5 | Framework Setup | Response Templates | Connect to ML Model | Test Responses | Fine-tune
3 | T-02 | Ticket submission and tracking UIUser-friendly interface with status updates | 2025-08-21 | 2025-08-23 | Nidhi | Design | Completed | 3 | Layout Design | Component Development | Backend Integration | UI Testing | Adjustments
4 | T-03 | Integration of ML model & UI for smart suggestionsShow predicted resolution to support agents | 2025-08-24 | 2025-08-26 | Nidhi | Coding | Completed | 6 | API Setup | Model Linking | UI Binding | Integration Testing | Bug Fixes
5 | T-04 | RAG-based sentiment & context analyticsDetect ticket urgency and sentiment | 2025-08-27 | 2025-08-29 | Nidhi | Coding | Completed | 9 | Data Setup | Embedding Test | Model Tuning | Sentiment Analysis | Evaluation
6 | T-05 | Coverage analysis for ticket categoriesIdentify areas with low ticket coverage | 2025-08-30 | 2025-08-31 | Nidhi | Coding | Completed | 10 | Data Aggregation | Analysis Scripts | Generate Metrics | Review Coverage | -
7 | T-06 | Low & high coverage alertsNotify managers when coverage is below or above thresholds | 2025-09-01 | 2025-09-02 | Nidhi | Coding | Completed | 10 | Define Thresholds | Alert Logic Coding | Test Alerts | - | -
8 | T-07 | Manager insights dashboardVisualize ticket metrics, coverage, and alerts | 2025-09-01 | 2025-09-02 | Nidhi | Design | Completed | 7 | Data Pipeline | Draft Charts | Metric Calculations | Testing | Review
9 | T-08 | Real-time recommendation engine for ticket suggestionsProvide smart article suggestions during ticket handling | 2025-09-27 | 2025-09-30 | Nidhi | Coding | Planned | 9 | Data Collection | Model Training | API Setup | Integration Testing | Validation
10 | T-09 | Track article usage and engagementIdentify frequently used or ignored articles | 2025-09-27 | 2025-09-30 | Nidhi | Analytics | Planned | 8 | Logging Setup | Interaction Tracking | Metrics Generation | - | -
11 | T-10 | Content gap analysisHighlight missing or low-coverage support articles | 2025-10-01 | 2025-10-02 | Nidhi | Analysis | Planned | 6 | Data Aggregation | Gap Identification | Priority List | - | -
12 | T-11 | Dashboard integration for content gaps and recommendationsVisualize article performance and coverage alerts | 2025-10-01 | 2025-10-02 | Nidhi | Design | Planned | 5 | Dashboard Update | Chart Development | Integration Testing | Testing | Review
13 | T-12 | End-to-end testing of recommendation engine, alerts, and dashboardValidate accuracy, performance, and alert triggers | 2025-10-02 | 2025-10-02 | Nidhi | Testing | Planned | 5 | System Integration | Performance Validation | Alert Verification | Bug Fixing | Documentation

## Stand up meeting
Sprint | Day | Impediments | Action Taken
1 | 13th August | Guidelines to begin the work | Begin the work
2 | 22nd August | Discussion about workflow of the project and Sprint 1 | Created Dataset requiring for sprint 1
3 | 4th September | Analysis about model and Discussion about sprint 2 | Connected Model to Google sheet and Started developing the UI
4 | 14th september | Reasoning about the lower accuracy and quota exccedence | Changed the chat and embedding Model
5 | 22nd September | Discussion about sprint 3 and alert system | Did the coverage analysis for the alert system
6 | 30th september | Finalizing the UI and making necessary Corrections | Finalizesd UI and made necessary changes

## Retrospection
S.No | Sprint | Start Date | End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 13 Aug | 22 Aug | Nidhi | ML model coding | - | Setup experiments | Initial model completed
2 | 2 | 22 Aug | 04 Sep | Nidhi | UI for ticket submission | - | Review process | UI established
3 | 3 | 04 Sep | 14 Sep | Nidhi | Integration of ML & UI | ML-only approach | Module integration | Integration successful
4 | 4 | 14 Sep | 22 Sep | Nidhi | RAG system improvements | UI tweaks | RAG enhancements | RAG analytics improved
5 | 5 | 22 Sep | 30 Sep | Nidhi | Dashboard features | Manual alert debugging | Tracking results | Dashboard finalized